## Action Planning
Talent Surge Playbook - Action Planning Template
Agency: |  | Plan Initiation:
Project Team: |  | Plan Completion:
This template has been constructed as a checklist to provide a way to strategically think through the hiring process and document when specific events will take place.
This should be used in conjunction with the Talent Surge Playbook for Rebuilding the Federal Workforce which contains information on HR flexibilities, authorities, actions, and other resources.
Workforce and Succession Planning Activities
Playbook Section | Action Steps | Owner | Success Measures | Status | Start Date | Anticipated Date Complete | Actual Date Complete | Comments
Plan | Conduct a strategic workforce meeting with identified entities that will be integral in the execution and success of the plan (e.g., CHCO, DCHCO, HR Manager, HR Specialist, recruitment, outreach and DEIA team members).
Plan | Assign tasks to team members and define responsibilities for executing the plan.
Plan | Review workforce succession and staff acquisition plans.
Hire | Prepare for future workforce needs via succession planning that may include the use of hiring flexibilities to fill mission critical positions.
Hire | Incorporate the use of hiring flexibilities to meet your agency strategic plan and Human Capital Plan.
Hire | Use existing hiring authorities to evaluate staffing needs and the most effective means of meeting those needs.
Hire | Develop processes to determine if former employees are reinstatement eligible (e.g., ensure performance was at least fully successful, separation was not due to adverse action procedures).
Plan | Identify resources available to support hiring efforts and any associated personnel vetting (suitability, national security, PIV credentialing) resource needs.
Plan | Identify knowledge, skills, and abilities required and on hand and identify gaps and/or imbalances that need to be addressed.
Plan | Periodically review workforce competencies to assess gaps.
Plan | Update existing and/or develop new competency models especially if the agency has not advertised a particular occupation recently.
Plan | HR and Hiring Manager ensure the position descriptions are accurate and up to date or revise position descriptions. This includes reviewing the position designation, as applicable.
Recruit | Examine job announcements and position descriptions to ensure gender-neutral, inclusive, and plain language.
Plan | Identify any applicable collective bargaining obligations or agreement requirements on merit promotion, position descriptions, and other relevant hiring matters.
Recruitment Strategy Activities
Playbook Section | Action Steps | Owner | Success Measures | Status | Start Date | Anticipated Date Complete | Actual Date Complete | Comments
Recruit | Develop an agency "brand" and branding strategies to build capacity with employees and potential applicants. Large agencies may want to develop an agency brand in addition to brands for bureaus and component agencies. Generally the brand showcases the agency mission.
Recruit | Create recruitment materials that reflect the brand.
Recruit | Assess whether recruitment materials are effective in attracting a broad range of talent.
Recruit | Enhance recruitment and branding efforts by producing videos of agency employees, providing a realistic preview for advertising positions.
Plan | Identify occupations that are experiencing particular hiring challenges and focus on root cause analysis and problem-solving in those areas.
Plan, Recruit | Develop a recruitment strategy that will support the agency talent acquisition process from initial job seeker interest through onboarding.
Plan | Identify sources for recruitment.
Plan, Recruit | Market potential workforce flexibilities such as telework, remote work, and flexible and compressed work schedules.
Recruit | Market comprehensive compensation and benefits packages.
Recruit | Use available recruitment flexibilities, such as recruitment and relocation incentives, strategically to attract new hires.
Hire | Develop an outreach plan for reaching eligible former employees.
Hire | Educate HR staff and hiring managers about the use of better assessments and the full range of hiring authorities available.
Hire | Provide training for staff on the use of talent acquisition systems to provide an improved user experience and leverage new tools in search of talent.
Plan | Develop a plan to identify current internal agency employees that are underutilized, or can be better realigned or reassigned to fill current mission critical vacancies.
DEIA Strategy Activities
Playbook Section | Action Steps | Owner | Success Measures | Status | Start Date | Anticipated Date Complete | Actual Date Complete | Comments
Recruit | Define agency DEIA recruitment strategy goals such as creating an agency brand that emphasizes diversity, filling positions with more diverse candidates, capturing more quality candidates from underserved and under-represented groups.
Recruit | Develop an agency outreach and recruitment plan with appropriate resources and approaches to enable the agency to reach specified goals (e.g., seek a diverse applicant pool).
Recruit | As part of an overall recruitment strategy, engage and partner with diverse organizations, including, but not limited to educational institutions, as potential sources of talent.
Recruit | Provide training for selection panels and hiring officials to cultivate inclusivity and support diversity in talent selection.
Hire | Leverage partnerships with Historically Black Colleges and Universities, including Historically Black Graduate Institutions; Hispanic -Serving Institutions; Tribal Colleges and Universities; Native American-serving, nontribal institutions; Asian American and Pacific Islander-serving institutions; Alaskan Native-serving and Native Hawaiian-serving institutions; community colleges and technical schools, and community-based organizations that are dedicated to serving and working with underserved communities as part of a comprehensive scheme to reach all segments of society.
Hire | Leverage the Workforce Recruitment Program (WRP) to connect with college students and recent graduates with disabilities.
Recruit | Conduct outreach to specific communities (e.g., Veterans and Military Spouses, students, persons with disabilities), utilizing data-driven methods and incorporating promising practices.
Hire | Leverage partnerships with Veterans Service Organizations, including Student Veteran of America and Iraq and Afghanistan Veterans of America, and other resources including Syracuse University's Institute of Veterans and Military Families.
Recruit | Leverage opportunities to recruit in the local commuting area, including attending or hosting virtual information events, conducting campus recruitment, and conducting outreach to relevant communities.
Recruit | Once the appointment process is complete, review applicant flow data for mission critical occupations to evaluate recruitment effectiveness and talent pool diversity.
Recruit | Expand the use of applicant flow data and analytics about the use of data to inform future outreach and recruitment decisions.
Recruit | Engage labor unions, where appropriate, on development of agency outreach and recruitment plan.
Assessment Strategy Activities
Playbook Section | Action Steps | Owner | Success Measures | Status | Start Date | Anticipated Date Complete | Actual Date Complete | Comments
Assess | Create a climate of change. Encourage and promote the use of assessments.
Assess | Create a climate of change. Raise awareness of the full range of hiring authorities and assessment options.
Assess | Target key job series or competency areas driven by agency mission for the development of assessments.
Assess | Leverage assessment experts to develop professional assessments.
Assess | Use the resources provided in the Assessment and Selection section of OPM.gov to improve the assessment of technical skills.
Assess | Leverage governmentwide competency data (MOSAIC Competencies).
Assess | Expand the use of better assessment options to improve the quality of hires.
Assess | Reduce reliance on self-rated questionnaires solely and promote the use of a variety of assessments and or multiple hurdles, which may include SME-QA, Structured Interviews and Writing Samples (e.g., written prompt exercise), Assessment vendors such as USA Hire.
Assess | Engage and enable - Governmentwide policy, educational initiatives, and assessment tools to facilitate the implementation of assessments.
Assess | Engage and enable - Improve skills of HR Professionals to effectively advise managers on all available hiring options.
Assess | Implement and Sustain - Review and analyze the use of educational initiatives, assessment tools, and policy guidance to increase quality hires governmentwide.
Assess | Implement and Sustain - Provide evidence-based data to support the use of assessment policy, practices, and tools for flexible staffing options.
Hiring Activity Strategy
Playbook Section | Action Steps | Owner | Success Measures | Status | Start Date | Anticipated Date Complete | Actual Date Complete | Comments
Plan | Promote active participation by hiring managers in the hiring process.
Hire | Use the Pathways Program to hire Recent Graduates, Presidential Management Fellows (PMFs), and Interns to develop talent.
Hire | Use newly issued authorities for Hiring Authority for Post-Secondary Students and Hiring Authority for College Graduates.
Hire | Use the recently amended reinstatement regulations that permit re-appointment to a permanent position at a higher grade where appropriate.
Recruit | Utilize non-competitive special hiring authorities such as Veterans Recruitment Authority, the hiring authority for 30% or more disabled Veterans, the military spouse hiring authority, and the Schedule A authority for individuals with certain disabilities.
Recruit | Promote opportunities on social media networks, at events, and on job boards visited by a diverse demographic.
Recruit | Use Department of Defense - Operation Warfighter (OWF) and SkillBridge Program, as well as the Department of Veterans Affairs - Non-paid Work Experience Program (NPWE) and Disabled Veterans in a Training Program (OJT) as appropriate, to help meet mission critical occupational need.
Hire | Identify opportunities to share certificates across your agency or through interagency efforts under the Competitive Service Act of 2015 and its implementing regulations.
Plan | HR and Hiring Manager create a job analysis by examining the tasks performed in a job, the critical competencies required to perform those tasks, and the connection between the tasks and the competencies.
Assess | Assessment strategy should describe the hiring situation (e.g., budget, time frame, volume of applicants).
Assess | Assessment strategy should determine how to assess (e.g., which competencies to include and which assessment tool to use).
Assess | Assessment strategy should determine the assessment process (e.g., passing grade plus relative scoring options or order of administered assessments).
Plan | HR and Hiring Manager/SMEs participate in identifying/developing the assessment tool (e.g., structured interviews, writing samples, tests) that will be used to screen for a passing grade and evaluate candidates' relative level of knowledge, skills, and abilities.
Plan | Update existing and/or develop new assessments especially if the agency has not advertised a particular occupation recently.
Plan | HR and Hiring Manager ensure that the JOA accurately describes the duties of the position and competencies and experience required in an easy-to understand and appealing manner.
Recruit | Use USAJOBS Agency Talent Portal to search for job seekers and invite them to apply to job opportunities.
Recruit | Use Resume Mining on USAJOBS to reach active job seekers for specialized needs and specialized hiring authorities.
Plan | After the applicants are assessed and the referral list is issued, the hiring manger actively engages in considering top candidates and making selections.
Plan | Include in all JOAs whether the position is included in a bargaining unit or not and, if included, identify the name and local or chapter number of the union representing the position being advertised.
Hire | Consider utilizing federal vetting policy flexibilities that permit individuals to onboard prior to completion of the background investigation, including national security positions when necessary for meeting mission readiness requirements.
Hire | Contact DCSA for assistance with background investigations for surge hiring.
Hire | Utilize OPM surge examining and onboarding support for agencies whose hiring demands exceed their internal HR capacity. This service is available through OPM Human Resources Solutions.
Retention Strategy Activities
Playbook Section | Action Steps | Owner | Success Measures | Status | Start Date | Anticipated Date Complete | Actual Date Complete | Comments
Recruitment and Retention Strategies | Develop a strong on-boarding process that fosters a sense of community within the agency.
Recruitment and Retention Strategies | Communicate to employees how their work fits in and contributes to the agency's goals and priorities.
Recruitment and Retention Strategies | Develop policies and programs that promote diversity and inclusion in the workplace. Where appropriate, engage labor unions in development and implementation of these policies and programs.
Employee Experience | Encourage and leverage participating in various employee resource groups (ERGs).
Employee Experience | Actively engage in building a strong, diverse group of future leaders.
Recruitment and Retention Strategies | Mentor employees to help advance their careers and build networks.
Recruitment and Retention Strategies | Offer opportunities for career growth and improvement in skills, including formal training and on-the-job learning and development. Such opportunities could encompass short-term learning experiences, projects, details, and mentoring opportunities through USAJOBS Open Opportunities. Where appropriate, determine any appropriate collective bargaining obligations or applicable collective bargaining agreements covering such matters.
Employee Experience | Demonstrate the value of learning and development by providing time, support, and resources for employees and managers to participate in these activities.
Employee Experience | Utilize the full-range of development options including low-cost or no-cost options such as rotations, lunch and learn sessions, and on-the-job learning experiences.
Employee Experience | Encourage employees to work with their managers to enhance their learning and growth by approving their participation in training courses within the Learning Management Systems and putting knowledge into practice through USAJOBS Open Opportunities short-term projects, details, and mentoring connections.
Recruitment and Retention Strategies | As appropriate, consider offering workforce flexibilities such as alternative work schedules (e.g., flexible work hours/days), telework and remote work.
Recruitment and Retention Strategies | Offer leave options that promote work-life balance.
Leave and Compensation | Support employees' ability to effectively manage their work and personal responsibilities with leave policies and programs and workforce flexibilities that promote work-life balance.
Recruitment and Retention Strategies | Utilize compensation flexibilities which may include: recruitment incentives, retention incentives, relocation incentives, federal student loan repayment program, special rates, superior qualifications and special needs pay-setting authority, creditable service for annual leave accrual, critical pay.
Leave and Compensation | Use discretionary authorities to provide additional direct compensation in certain circumstances to support recruitment, relocation, and retention efforts.
Leave and Compensation | Ensure compensation flexibilities are used judiciously and in accordance with applicable laws, regulations, agency policy, collective bargaining agreements, and budgetary limitations.
Recruitment and Retention Strategies | Assess the success of the use of non-monetary strategies and factors.
Employee Experience | Create feedback mechanisms for communication between employees and leadership.

## Vacancy Checklist
Target Number of Hires:
Targeted Occupations:
Position Title | Organization Office/Division | Series | Grade | Full Performance Level | # of Selections Approved | Location(s) | Status | PD accurate and up to date | List Hiring Authorities Chosen | Describe Recruitment Strategy | Leave and/or Compensation Incentives included | Work/Life Balance Incentives included | Job Analysis Complete | Assessment(s) developed | JOA drafted and approved | Open Date | Close Date